## Week 1
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 1
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-02-26
Tuesday | 2018-02-27 | 16:00 | 17:00 | 1 | 1. Team and topic's arrangement. 2. Discuss how to get familiar with this topic as next step. | Teamwork is efficient and we have an initial concept about this topic. | 1. Search information about Network Forensics on Internet, then I listed some questions 2. Email tutor to book a meeting(4:30 pm) next day
Wednesday | 2018-02-28 | 16:30 | 20:00 | 3.5 | 1. Have a meeting with tutor Faheem. 2. Continue working on seraching information | 1. Work on the core part of this project. 2. Choosing platform and language to prepare this task | 1. Knowed the most important part we need to study and solve analyse system's problems. 2. Using Java and hadoop as our tools
Thursday | 2018-03-01 | 17:30 | 18:00 | 0.5 | 1. Searching information about hadoop | 1. Build the platform for this project | Working on it
Friday | 2018-03-02 | 14:00 | 16:00 | 2 | 1. Study the hadoop setup tutorial which is from Faheem | Build the environment for hadoop | Have basic concepts of Hadoop
Saturday | 2018-03-03 | 21:00 | 23:30 | 2.5 | 1. Build the environment for hadoop | Build the environment for hadoop | 1. Succeed to build the environment for hadoop. 2. I will have some tests for hadoop distributed system, like the Wordcount.java
|  |  | Total | 9.5

## Week 2
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-03-05 | 15:00 | 16:00 | 1 | Test hadoop running environment | Hadoop is a basic platform in this project | I can use wordcout.java to calculate the total number of each word by running hadoop
Tuesday | 2018-03-06 | 15:30 | 17:30 | 2 | Learned and discussed how to develop Pitch presentation and ppt with my teammate | This taks could help us to figure it out why the network forensics analysis system is useful and what the system is. | Got the basic requiremnts and guidance for this presentation.
Wednesday | 2018-03-07 | 18:30 | 21:00 | 2.5 | Collected the useful data about network forensics'background and made the Pitch ppt draft. | It is the first mission for this project. | Pitch_draft.ppt(why part)
Thursday | 2018-03-08 | 14:00 | 17:00 | 3 | Learned the HDFS concepts and running some revelant programs. Test mapreduce in hadoop. | HDFS is the basic tool for storing numerous data. And mapreduce is the core for dealing with huge data. | Got familiar with HDFS basic commands and fundemental skills. Run the mapreduce_examples to wordcount.
Friday | 2018-03-09 | 14:00 | 16:00 | 2 | Studied the requirements about this network forensics analysis system | Build the system to meet client's requirements. | 1. accuracy 2. latency-time
Saturday | 2018-03-10 | 11:00 | 13:30 | 2.5 | Modified Pitch_draft.ppt and learned system structure online. | Pitch for presentation and structure is important for project's system | 1. Pitch.ppt 2. Structure draft.
|  |  | Total | 13

## Week 3
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-03-12 | 12:00 | 17:00 | 5 | 1.Modify the PPT according to the tutor's suggestions 2.write the Agenda | To get a better performance of presentation in next weeek 2.Listed all the questions and findings to ask advice from client | Delete some slides and add more details as explanations. Then start to write the speech card for the presentation 2.Agenda
Tuesday | 2018-03-13 | 15:00 | 17:30 | 2.5 | Meeting with client | Solving the problems and answering the questions we found during the plan | Providing more information for us such as some research paper and particular algorithms for us as options
Wednesday | 2018-03-14 | 14:30 | 21:00 | 6.5 | Finding the specific usages and theories of the algorithms | Maybe we could find a suitable one to fit our project | C4.5 & Apriori & ANOVA (may choose C4.5)
Thursday | 2018-03-15 | 13:00 | 17:00 | 4 | Study the research paper | The revelant algorithms are explained in these papers | Find the most suitable one to use in our project
Friday | 2018-03-16 | 15:00 | 17:00 | 2 | Modify the slides | Before the submission, make some adjustments to improve the quality of PPT | Finish the reason part, summary is still needed to be modified
Saturday | 2018-03-17 | 9:00 | 12:00 | 3 | Practiced the presentation with teammate | Checked the checklist to ensure meet all the requirements | Need client's recommendations
|  |  | Total | 23

## Week 4
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-03-19 | 13:00 | 18:00 | 5 | 1.Practiced the pitch presentation speech 2.Write the Agenda | 1.Explain why we should develop and implement our detection system 2.Listed the questions about pitch presentation | 1.Will give a presentation tommorrow afternoon 2.Agenda
Tuesday | 2018-03-20 | 15:00 | 16:30 | 1.5 | Meeting with client | Show the final PPT to client | Got some suggestions from client
Wednesday | 2018-03-21 | 15:00 | 19:30 | 4.5 | 1.Discussed the milestone 1 plan with teammate 2.Write the meeting minutes | 1.We need to complete the jobs according to the milestone 1 plan 2.Record the solutions discussed in meeting | 1.Listed the basic requirements must be meeted and some ideas of our system 2.Minutes
Thursday | 2018-03-22 | 14:00 | 19:00 | 5 | Read some research paper to study algorithm C4.5 | It is the core algorithm for our project | Knowed the Gain's meaning and how to use it
Friday | 2018-03-23 | 12:00 | 19:00 | 7 | Searching the C4.5 algorithm implemented on Hadoop platform | One of our plan is implementing the algoritm on the Hadoop to improve the performance | Found some source codes which could be used on Hadoop
Saturday | 2018-03-24 | 11:00 | 17:30 | 6.5 | 1.Learning how to implement the C4.5 algorithm basic on Hadoop 2.Write business case | 1.Using this algorithm to achieve the detection 2. This document decribes the whole project's process and the time schedule | 1.Still need to learn the algorithm 2.Write some parts of this document
|  |  | Total | 29.5

## Week 5
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-03-26 | 15:00 | 19:30 | 4.5 | 1.Write the business case 2.Write the Agenda | 1.The whole project's precess and time schedule 2.Listed the question and troblems we meet in coding | 1.Nearly finished the busness case 2.Agenda
Tuesday | 2018-03-27 | 15:00 | 16:30 | 1.5 | Meeting with client | 1.Show our project's current stage to client 2.Questions about business case | Got recommendations about business case and our system from client
Wednesday | 2018-03-28 | 17:00 | 21:00 | 4 | 1.Modified the business case and add the time schedule chart 2. Write the meeting minutes | 1.The business case second part need to list the detailed workload arrangment 2.Record the solutions and findings from meeting | BusinessCase.pdf & Minutes
Thursday | 2018-03-29 | 12:00 | 15:00 | 3 | Searching information decision tree pruning algorithm to solve the overfiting issue | The values are discrete, others are continuous | Find the way to set a range
Friday | 2018-03-30 | 23:00 | 14:00 | 3 | Implementing the code | to achieve the detection system | Problems occurred
Saturday | 2018-03-31 | 10:00 | 12:30 | 2.5 | Tried to train the model | Train the model first then we could use it to detect the attacks | Still working on it
|  |  | Total | 18.5

## Mid-break1
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Mid-break1
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-04-02 | 15:00 | 16:30 | 1.5 | 1.Compare the KDD dataset's parameters to find the useless ones 2.Write the Agenda | 1.Some parameters are useless that affect the response time 2.Listed the question and troblems we meet in coding | 1.Manually delete the useless parameters is impossible 2.Agenda
Tuesday | 2018-04-03 | 15:00 | 16:30 | 1.5 | Meeting with client | Show our project's current stage to client | The response time should be approximate 13 mins or less
Wednesday | 2018-04-04 | 12:00 | 17:00 | 5 | 1.Tried to find the way utilize the data to form the training model 2.Write the meeting minutes | 1.Using the training data to produce the model to test the testing data 2.Record the solutions and findings from meeting | 1.continue to study it 2.Minutes
Thursday | 2018-04-05 | 15:00 | 19:30 | 4.5 | Tried to implement the algorithm to build the model | Using the training data to produce the model to test the testing data | still working on it
Friday | 2018-04-06 | 16:00 | 18:00 | 2 | Build up the model by training data | Build the model for detection | still working on it
Saturday | 2018-04-07 | 11:00 | 14:30 | 3.5 | Have successfully utilize the training data to build the model by teammate, next will write the testing part | build the model with XML file to record the decision tree | Can have the detection rate, but still have problems
|  |  | Total | 18

## Mid-break2
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Mid-break2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-04-09 | 13:00 | 17:30 | 4.5 | 1.Tried to shorten the training time 2.Write the Agenda | 1.It cost more then 2 hours to build the model that is too long 2.Listed the question and troblems we meet in training time | 1.Not finish 2.Agenda
Tuesday | 2018-04-10 | 15:00 | 16:30 | 1.5 | Meeting with client | Show our project's current stage to client | We need to implement our system on Hadoop platform, not just the testing part
Wednesday | 2018-04-11 | 12:00 | 18:00 | 6 | 1.Tried to implement the C4.5 algorithm in Hadoop 2.Write the minutes | 1.Implement the code by using mapreduce should be faseter, especially incooperate with more computers 2.Record the suggestions and findings from meeting | 1.Found some source code implemneted the C4.5 algorithm based on Hadoop, but cannot handle the discrete values 2.Minutes
Thursday | 2018-04-12 | 13:00 | 18:30 | 5.5 | Modified the code to implement it on Hadoop | It is suitable for our project | Learning mapreduce from papers and source code
Friday | 2018-04-13 | 15:00 | 18:00 | 3 | Learning to use mapreduce to implement C4.5 algorithm | It could reduce the training time | Still working on it
Saturday | 2018-04-14 | 11:00 | 14:30 | 3.5 | Modified the code | It could reduce the training time | Not finished
|  |  | Total | 24

## Week 6
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-04-16 | 12:00 | 15:30 | 3.5 | 1.Modify the code 2.Write the Agenda | 1.Implement our code base on Hadoop platform 2.Listed the question and troblems we meet in coding | 1.Still working on it 2.Agenda
Tuesday | 2018-04-17 | 15:00 | 16:30 | 1.5 | Meeting with client | Show our project's current stage to client | Got recommendations about improving the code and know a new algorithm Xgboost
Wednesday | 2018-04-18 | 14:00 | 21:00 | 7 | 1.Build the Xgboost and Python running envirnment 2. Write the meeting minutes | 1.We will use another algorithm as comparison to C4.5 2.Record the suggestions and findings from meeting | 1.Python 3.5 is usable and xgboost package has been successfully installed 2.Minutes
Thursday | 2018-04-19 | 10:00 | 16:00 | 6 | Tried to implement the xgboost algorithm in Python | It is a new machine learning algorithm out of our plan | It seems that the xgboost algorithm just need to modify the parameters to run it
Friday | 2018-04-20 | 11:00 | 15:00 | 4 | Implementing the code | As a comparison to C4.5 algorithm | It can just use numbers to train the data
Saturday | 2018-04-21 | 14:00 | 16:30 | 2.5 | Tried to train the model | Train the model first then we could use it to detect the attacks | Still working on it
|  |  | Total | 24.5

## Week 7
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-04-23 | 11:00 | 16:30 | 5.5 | 1.Implementing the system 2.Write the Agenda 3. milestone 1 report | 1.It should detect the cyber-attacks as C4.5 system 2.Listed the question and troblems we meet in coding 3. reporting the progress | 1.Could build the tree in XML file 2.Agenda
Tuesday | 2018-04-24 | 15:00 | 16:30 | 1.5 | Meeting with client | Show our project's current stage to client | The Xgboost algorithm need to implemented in Hadoop as C4.5 system.
Wednesday | 2018-04-25 | 17:00 | 20:30 | 3.5 | 1.Learn how to build the recursive tree with understandable XML structure 2. Write the meeting minutes 3. milestone 2 plan | 1.The tree is hard to read 2.Record the suggestions and findings from meeting 3.Planning the next goals we want to achieve | 1.The structure of the tree is complecated. 2.Minutes
Thursday | 2018-04-26 | 11:30 | 15:00 | 3.5 | Try to implement the xgboost algorithm without using the default xgboost-package | Need to build the training model | Not finished yet, still working on it.
Friday | 2018-04-27 | 11:00 | 16:00 | 5 | Implementing the xgboost system | Main work in this system | Still working on it
Saturday | 2018-04-28 | 12:00 | 15:30 | 3.5 | Implementing the xgboost system | Main work in this system | Could build the tree but it has problems, still working on it
|  |  | Total | 22.5

## Week 8
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-04-30 | 10:30 | 13:30 | 3 | 1.Implementing the system 2.Write the Agenda | 1.Main work of this system 2.Listed the questions and troblems we meet in implementing the system | 1.Produce the wrong data, need to fix it 2.Agenda
Tuesday | 2018-05-01 | 15:00 | 16:30 | 1.5 | Meeting with client | Show our project's current stage to client | The Xgboost algorithm should be used in this system with mapreduce functions. It is a charllenging task that we will develop the system in Hadoop and Spark respectively.
Wednesday | 2018-05-02 | 16:00 | 20:30 | 4.5 | 1.Learn how to develop the system in Spark 2. Write the meeting minutes | 1.Xgboost also could be implemented in Spark 2.Record the suggestions and findings from meeting | 1.Set up the Spark running environment and download Scala 2.Minutes
Thursday | 2018-05-03 | 11:30 | 18:00 | 6.5 | Learn the language of Scala and Spark | Use these tools to develop our system | Trying to find the similarity of xgboost package using method between hadoop and Spark
Friday | 2018-05-04 | 11:00 | 16:00 | 5 | Tried to implement the xgboost algorithm in Spark | This is our system implementing another algorithm as comprison | Still working on it
Saturday | 2018-05-05 | 14:00 | 18:30 | 4.5 | Implementing the xgboost system in Spark | This is our system implementing another algorithm as comprison | Meet some problems, could not use the default xgboost4j package. Still working on it
|  |  | Total | 25

## Week 9
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-05-07 | 12:30 | 15:30 | 3 | 1.Implementing the system 2.Write the Agenda | 1.Main work of this system 2.Listed the questions and troblems we meet in implementing the system | 1.Could build the training model, but is not good as using in Hadoop 2.Agenda
Tuesday | 2018-05-08 | 15:00 | 16:30 | 1.5 | Meeting with client | Show our project's current stage to client | Showed the system implemented the xgboost algorithm in Hadoop. But we still need to improve the performance, the false positive rate is higher than C4.5 system
Wednesday | 2018-05-09 | 11:00 | 14:30 | 3.5 | 1.Read the false positive rate reduction papers 2. Write the meeting minutes | 1.Xgboost's performance is better than C4.5 in some situations, but false positive rate is higher than C4.5 system 2.Record the suggestions and findings from meeting | 1.Read related papers 2.Minutes
Thursday | 2018-05-10 | 17:30 | 21:00 | 3.5 | Tried to find another calculation and some techniques to reduce the false postive rate | Improving the performance of our system | Still working on it
Friday | 2018-05-11 | 15:00 | 19:00 | 4 | Modify the testing documents | The accuracy is important for our project | Modified some parts.
Saturday | 2018-05-12 | 13:30 | 16:30 | 3 | Write the milestone 2 report | Record the current progress and problems we meet | Still working on it
|  |  | Total | 18.5

## Week 10
MCI Project Weekly Time Sheet
Team | 19 | Student ID | a1698691 |  |  | Week starting: | Week 10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2018-05-14 | 14:30 | 18:30 | 4 | 1.Testing plan 2.Write the Agenda | 1.Make the plan to test our system to ensure we meet all the requirements of this project 2.Listed the questions and troblems we meet in implementing the system | 1.Still work on it 2.Agenda
Tuesday | 2018-05-15 | 15:00 | 16:30 | 1.5 | Meeting with client | Show our project's current stage to client | Some suggestions from client about our training part and our testing data format.
Wednesday | 2018-05-16 | 11:00 | 16:30 | 5.5 | 1.GUI design 2. Write the meeting minutes | 1.A GUI for demonstration is necessary 2.Record the suggestions and findings from meeting | 1.Working on produce a prototype of GUI 2.Minutes
Thursday | 2018-05-17 | 16:30 | 20:00 | 3.5 | Implementing a GUI for our system | Easy for us to operate and demonstrate our system for people and it is an extension | Still working on it
Friday | 2018-05-18 | 14:00 | 19:00 | 5 | 1. Write the milestone 2 report 2. Implementing a GUI for our system | 1. It is about our current progress status 2. GUI is an extension for our project | Still working on both
Saturday | 2018-05-19 | 12:30 | 16:30 | 4 | Write the milestone 2 report | It is about our current progress status | Finished and uploaded.
|  |  | Total | 23.5