## Sheet2
MCI Project Weekly Time Sheet
Team | 19 | Student ID |  | a1710525 |  | Week starting: | middlebreak1
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2018-04-02 | 16:00 | 22:00 | 6 | implementing the code of c4.5 in java | this is the main part of the project | not finished yet. Since I've never used java before, I spent half of my time in learning java while coding.
Tuesday | 2018-04-03 | 3:00 | 4:30 | 1.5 | regular meeting with client | showing the progress of our project to the client. | We talked about the problem we encountered. I will continue implementing the code.
Wednesday | 2018-04-04 | 18:00 | 20:45 | 2.75 | implementing the code of c4.5 in java | this is the main part of the project | not finished yet. Will continue doing it tomorrow
Thursday | 2018-04-05 | 15:00 | 20:30 | 5.5 | implementing the code of c4.5 in java | this is the main part of the project | not finished yet. Will continue doing it tomorrow
Friday | 2018-04-06 | 16:00 | 20:00 | 4 | implementing the code of c4.5 in java | this is the main part of the project. | Finished. Now it can print out a XML file showing the tree structure which can be test with the testing data set.
Saturday | 2018-04-07 | 14:00 | 20:15 | 6.25 | implementing the testing code of output result in java | I found a testing part on GitHub but it is implemented in python. Our project has to be run on Hadoop and java, so I decide to write my own code. | Finished. It can now print out the error rate.
|  |  | Total | 26