## Sheet2
MCI Project Weekly Time Sheet
Team | 19 | Student ID |  | a1710525 |  | Week starting: | middlebreak2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2018-04-09 | 16:15 | 22:00 | 5.75 | adjust the code structure to see if it can be faster. | the training time is quite long because of the feature of the data set. This data set has a huge range of numeric attributes. The code can be changed agaist this feature. | I improved this algorithm.
Tuesday | 2018-04-10 | 3:00 | 4:15 | 1.25 | regular meeting with client | showing the progress of our project to the client. | the format of testing result is not quite right. The client gave me some papars to change the format. The client thinks the training part( c4.5) has to be implemented in hadoop as well.
Wednesday | 2018-04-11 | 13:00 | 20:00 | 7 | transplanting the code to hadoop | Our project is incorporating the hadoop software and the machin learing algorithm so it has to be on hadoop | not finished yet. Will continue doing it tomorrow
Thursday | 2018-04-12 | 14:00 | 20:30 | 6.5 | transplanting the code to hadoop | this is the main part of the project | not finished yet. It is bit difficult to rewrite the code on hadoop, because I have to follow the logic sequence of how hadoop processing data.
Friday | 2018-04-13 | 16:00 | 20:00 | 4 | transplanting the code to hadoop | this is the main part of the project. | not finished yet. Will continue doing it tomorrow.
Saturday | 2018-04-14 | 15:00 | 20:00 | 5 | transplanting the code to hadoop | this is the main part of the project. | not finished yet. Will continue doing it tomorrow
|  |  | Total | 29.5