## Sheet2
MCI Project Weekly Time Sheet
Team | 19 | Student ID |  | a1710525 |  | Week starting: | 10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2018-05-14 | 16:15 | 20:00 | 3.75 | writing testing plan for the project | the testing plan is for testing the system to see if it has meet the requirement of client | had a draft plan now needing polishing.
Tuesday | 2018-05-15 | 3:00 | 4:45 | 1.75 | regular meeting with client | showing the progress of our project to the client. | the format of testing result is not quite right. The client gave me some papers to change the format. The client thinks the training part( c4.5) has to be implemented in Hadoop as well.
Wednesday | 2018-05-16 | 17:00 | 20:00 | 3 | writing testing plan for the project | the testing plan is for testing the system to see if it has meet the requirement of client | finished. Will send it to client for some feedbacks
Thursday | 2018-05-17 | 12:00 | 18:30 | 6.5 | writing the milestone 2 report | this is the report for the progress so far. It is used to get feedback from client and lecturers. | not finished yet. It needs polishing.
Friday | 2018-05-18 | 16:00 | 20:30 | 4.5 | testing the system | testing results will be an important part of the final report and presentation | not finished yet.
Saturday | 2018-05-19 | 16:15 | 21:00 | 4.75 | writing the milestone 2 report | this is the report for the progress so far. It is used to get feedback from client and lecturers. | finished. Will send it to client for some feedbacks
|  |  | Total | 24.25