## Sheet2
MCI Project Weekly Time Sheet
Team | 19 | Student ID |  | a1710525 |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2018-03-26 | 16:00 | 20:00 | 4 | writing business case | it is a document describing the project | send it to client for some advice
Tuesday | 2018-03-27 | 3:00 | 4:15 | 1.25 | regular meeting with client | discussing about the business case with client. Showing current progress of the project | received some advice to improve the busines case
Wednesday | 2018-03-28 | 16:00 | 19:45 | 3.75 | reviseing business case and draft plan | making the business case more appliable to the project | the business case and draft plant is finished
Thursday | 2018-03-29 | 13:00 | 18:30 | 5.5 | implementing the code of c4.5 in java | this is the main part of the project. Because it is not implemented by anyone else before, I have to do it myself | not finished yet. Will continue doing it tomorrow
Friday | 2018-03-30 | 14:00 | 20:00 | 6 | continue implementing the code of c4.5 in java | this is the main part of the project | not finished yet.
Saturday | 2018-03-31 | 13:00 | 20:15 | 7.25 | continue implementing the code of c4.5 in java | will finish it first then apply it to hadoop. | it is finished now. Will show the result to the client next week
|  |  | Total | 27.75