## Sheet2
MCI Project Weekly Time Sheet
Team | 19 | Student ID |  | a1710525 |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2018-04-23 | 13:15 | 16:30 | 3.25 | polishing the milestone 1 report. | this is the report for the progress so far. It is used to get feedback from client and lecturers. | submiited the report.
Tuesday | 2018-04-24 | 3:00 | 4:30 | 1.5 | regular meeting with client | showing client the system by official library. | client thought the system should be on distributed system as same as the first system.
Wednesday | 2018-04-25 | 14:00 | 18:00 | 4 | preparing the milestone 2 plan | this plan is a draft plan for milestone 2 | it is finished and accepted by client
Thursday | 2018-04-26 | 16:00 | 20:30 | 4.5 | trying to deploy the system on distributed file system | the system can run on distributed file system | not finished yet. Tried to build it on local pseudo distributed system but failed.
Friday | 2018-04-27 | 16:00 | 20:00 | 4 | implementing the system in Hadoop | the system can run on distributed file system | tried to build it on AWS EC2 platform. Not finished yet. Will continue doing it tomorrow.
Saturday | 2018-04-28 | 13:00 | 20:00 | 7 | implementing the system in Hadoop | the system can run on distributed file system | not finished yet. Will continue doing it tomorrow
|  |  | Total | 24.25