## Sheet2
MCI Project Weekly Time Sheet
Team | 19 | Student ID |  | a1710525 |  | Week starting: | 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2018-04-30 | 13:15 | 18:00 | 4.75 | implementing the system in Hadoop | this is the main part of the project. | not finished yet because the environment is different and AWS is expensive
Tuesday | 2018-05-01 | 3:00 | 4:30 | 1.5 | regular meeting with client | showing the progress of our project to the client. | client thought the system should be wrote with map-reduce as same as the first system. Made multi-level plan with client because this algorithm is harder than the first one. We are not sure if we can finish it in time.
Wednesday | 2018-05-02 | 16:00 | 20:30 | 4.5 | implementing the system in Hadoop | this is the main part of the project. The system will be implemented with map-reduce model | not finished yet. It is very challenging to write the code because there is very little resource available
Thursday | 2018-05-03 | 16:15 | 20:30 | 4.25 | implementing the system in Hadoop | this is the main part of the project | not finished yet. Will continue doing it tomorrow
Friday | 2018-05-04 | 16:00 | 19:00 | 3 | implementing the system in Hadoop | this is the main part of the project. | not finished yet. Will continue doing it tomorrow.
Saturday | 2018-05-05 | 13:00 | 19:00 | 6 | implementing the system in Hadoop | this is the main part of the project. | nearly finished. Had some of the basic functions now.
|  |  | Total | 24