## Sheet2
MCI Project Weekly Time Sheet
Team | 19 | Student ID |  | a1710525 |  | Week starting: | 9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2018-05-07 | 16:15 | 21:00 | 4.75 | implementing the system in Hadoop | this is the main part of the project. | partially finished. It is not the same as official project but can meet the requirement of client
Tuesday | 2018-05-08 | 3:00 | 4:15 | 1.25 | regular meeting with client | demonstrating the system to client. showing the progress of our project to the client. | client thought the current system is good but we need added more functions to it and we can possibly use some post-processing technique to get better performance.
Wednesday | 2018-05-09 | 16:00 | 20:00 | 4 | integrating the system to make it act the same as the official project | the function we have the better performance we can possibly get | not finished yet. Will continue doing it tomorrow
Thursday | 2018-05-10 | 14:00 | 20:30 | 6.5 | integrating the system to make it act the same as the official project | the function we have the better performance we can possibly get | not finished yet. Will continue doing it tomorrow
Friday | 2018-05-11 | 16:00 | 20:15 | 4.25 | starting to write the milestone 2 report | this is the report for the progress so far. It is used to get feedback from client and lecturers. | had a draft report now needing polishing.
Saturday | 2018-05-12 | 15:00 | 20:15 | 5.25 | integrating the system to make it act the same as the official project | the function we have the better performance we can possibly get | finished. Now it can be tested with different initial input
|  |  | Total | 26